## Alpha
ALPHA - DSR - 18/8
S.No | Team | ID | Project Name | Subject | CB | ET | RT | Priority | Current status | AT taken | AT% | P% | E%
1 | Alpha | TS23863 | Shaher_ERP_15.10.2024 | Need to remove the restriction in Leave Applicable will be applied for 30 days except for company Shaher | GP | 0.5 | 0.5 | High | Pending Review | 0.27 | 54 | 85.15% | 111.9%
2 | Alpha | TS23774 | Internal ERP - TEAMPRO V15 | Updates in IT dashboard | GP | 3 | 1.8 | High | Pending Review | 2.2 | 73.3333
3 | Alpha | TS23874 | Shaher_ERP_15.10.2024 | Need to check the Leave Balance SUOM484, SU420 | GP | 0.5 | 0.5 | High | Pending Review | 0.85 | 170
4 | Alpha | TS23784 | Shaher_ERP_15.10.2024 | Leave salary coming wrong | GP | 1 | 1 | Medium | Pending Review | 0.52 | 52
5 | Alpha | TS23742 | Shaher_ERP_15.10.2024 | Need to check the Activity Log of Ali Hassan Sahi | GP | 0.5 | 0.5 | Medium | Pending Review | 0.97 | 194
6 | Alpha | TS23746 | Shaher_ERP_15.10.2024 | Need to give a Bar Code for Asset Item | GP | 0.75 | 0.75 | High | Working | 0.84 | 112
7 | Alpha | TS23886 | RANK_ERP_07.04.2025 | Meeting with ismail sir - 19/08 | PS | 0.5 | 0.5 | Medium | Completed | 0.46 | 92 | 70.02% | 74.83%
8 | Alpha | TS22909 | Shaher_ERP_15.10.2024 | Financial Audit dashboard - should have a drill down feature to get into details. | PS | 4 | 1.62 | Medium | Pending Review | 3.41 | 85.25
9 | Alpha | TS22914 | Shaher_ERP_15.10.2024 | In all documents, both foreign currency and local currency should be available in case of dealing with foreign vendors and customers. | PS | 2 | 2 | Medium | Pending Review | 0 | 0
10 | Alpha | TS23859 | Shaher_ERP_15.10.2024 | For the company Alpha - for the accounting documents (JV, SI,PI and Payment entry) need to remove signature | PS | 1 | 1 | Medium | Pending Review | 0.99 | 99
11 | Alpha | TS23868 | Shaya Polymers_HRPRO_21.11.25 | Need to update the biometric and user id details for the employees | PS | 1 | 1 | High | Pending Review | 0.86 | 86
12 | Alpha | TS23776 | Shaher_ERP_15.10.2024 | Payment cleared for the month of April in Profit and Loss report , the due is reflecting | PS | 1 | 0.62 | Medium | Working | 0.02 | 2
13 | Alpha | TS23882 | Shaher_ERP_15.10.2024 | Not able to save PO | PS | 0.5 | 0.5 | High | Working | 0.19 | 38
14 | Alpha | TS23883 | RANK_ERP_07.04.2025 | Need to create new company - Prime Doors Company | PS | 1.5 | 1.5 | High | Working | 0.61 | 40.6667
15 | Alpha | TS23786 | Norden_ERP_01.05.21 | In Stock as on 31 Dec 2024 8,845,054.13 but in ageing report 9,438,325.57 | TBA | 0.75 |  | Urgent | Client Review | 0.1 | 13.3333 | 41.07% | 75.87%
16 | Alpha | TS23865 | Internal ERP - TEAMPRO V15 | For Vending Machine template upload should be accept item code without - symbol. Need to check the teamplate shared by Kumaran Sir and Amirt | TBA | 1 | 1 | High | Pending Review | 1.47 | 147
17 | Alpha | TS23810 | JGB_ERP_Implementation_30/05/25 | In Purchase invoice stock billed account not come based on division. Need to check this | TBA | 1 | 1 | Medium | Pending Review | 0.86 | 86
18 | Alpha | TS23877 | JGB_ERP_Implementation_30/05/25 | Submit button not visible to user Shiyas in Purchase order 2506 | TBA | 0.5 | 0.5 | High | Pending Review | 0.39 | 78
19 | Alpha | TS23763 | Taihan_ERP_01.10.2024 | Need to create Print format for job card as per attachment.Barcode and Batch ID is must needed | TBA | 1.5 | 1.5 | High | Pending Review | 1.73 | 115.3333
20 | Alpha | TS23811 | JGB_ERP_Implementation_30/05/25 | Some delivery notes not connected with its sales order. | TBA | 1 | 0.74 | Medium | Working | 0 | 0
21 | Alpha | TS23812 | JGB_ERP_Implementation_30/05/25 | In Delivery note report, some delivery note was not billed due to decimal problem. Need to close that delivery note | TBA | 0.5 | 0.5 | High | Working | 0 | 0
22 | Alpha | TS23816 | JGB_ERP_Implementation_30/05/25 | For asset purchase invoice, need to get account asset received. | TBA | 0.5 | 0.5 | Medium | Working | 0 | 0
23 | Alpha | TS23869 | Norden_ERP_01.05.21 | For Stock Received and Not billed account how 25164015.47000006 this amount came as opening. Need to check | TBA | 1 | 1 | Urgent | Working | 2 | 200
24 | Alpha | TS23764 | Taihan_ERP_01.10.2024 | While creating the Stranding Material Transfer, we need to consider the full quantity produced for the Buffering item from the batch.For exa | TBA | 1 | 1 | Medium | Working | 0.84 | 84
25 | Alpha | TS23871 | TEAMPRO Website | Need to change Header size to small and In Common pages need to change images related to that website | TBA | 2 | 2 | Medium | Working | 0 | 0
ALPHA - DPR - 19/8
S.No | Team | ID | Project Name | Subject | CB | RT | Total RT | Priority
1 | Alpha | TS23896 | Shaher_ERP_15.10.2024 | Rejected Leaves are showing in Leave history of Leave Application | GP | 0.5 | 4.8 | High
2 | Alpha | TS23897 | Shaher_ERP_15.10.2024 | Rejected Leave Application notification | GP | 0.5 |  | High
3 | Alpha | TS23746 | Shaher_ERP_15.10.2024 | Need to give a Bar Code for Asset Item | GP |  |  | High
4 | Alpha | TS23602 | ELECTRA_ERP_07.06.2021 | Em# 006 â€“ Overtime calculation shows a difference of QAR 3. | GP | 0.66 |  | High
5 | Alpha | TS23899 | QPIC_ERP_10.04.22 | Need to check the PP fabric technical sheet and costing sheet | GP | 2 |  | Medium
6 | Alpha | TS23663 | Internal ERP - TEAMPRO V15 | Updates in AI Lead validation | GP | 1.14 |  | Medium
7 | Alpha | TS23891 | Galfar_PMS_12.03.26 | Need to update training data in appraisals | PS | 0.75 | 6.04 | High
8 | Alpha | TS23883 | RANK_ERP_07.04.2025 | Need to create new company - Prime Doors Company | PS | 0.89 |  | High
9 | Alpha | TS23892 | RANK_ERP_07.04.2025 | Need to connect with Ismail sir to cross check the chart of accounts | PS | 1 |  | Medium
10 | Alpha | TS22915 | Shaher_ERP_15.10.2024 | In case of bank balance, want to know below from system.Cheque prepared but not yet given to Vendor's with related details like cheque date, | PS | 0.5 |  | Medium
11 | Alpha | TS22927 | Shaher_ERP_15.10.2024 | they have around 43 documents to be implemented in ERP in which only 9 documents are available, need to bring the remaining documents.each d | PS | 1 |  | Medium
12 | Alpha | TS23776 | Shaher_ERP_15.10.2024 | Payment cleared for the month of April in Profit and Loss report , the due is reflecting | PS | 0.59 |  | Medium
13 | Alpha | TS23882 | Shaher_ERP_15.10.2024 | Not able to save PO | PS | 0.31 |  | High
14 | Alpha | TS23890 | Shaher_ERP_15.10.2024 | Not able to save leave salary documents | PS | 1 |  | High
15 | Alpha | TS23764 | Taihan_ERP_01.10.2024 | While creating the Stranding Material Transfer, we need to consider the full quantity produced for the Buffering item from the batch.For exa | TBA | 0.16 | 8.4 | Medium
16 | Alpha | TS23869 | Norden_ERP_01.05.21 | For Stock Received and Not billed account how 25164015.47000006 this amount came as opening. Need to check | TBA |  |  | High
17 | Alpha | TS23811 | JGB_ERP_Implementation_30/05/25 | Some delivery notes not connected with its sales order. | TBA | 0.74 |  | Medium
18 | Alpha | TS23812 | JGB_ERP_Implementation_30/05/25 | In Delivery note report, some delivery note was not billed due to decimal problem. Need to close that delivery note | TBA | 0.5 |  | High
19 | Alpha | TS23816 | JGB_ERP_Implementation_30/05/25 | For asset purchase invoice, need to get account asset received. | TBA | 0.5 |  | Medium
20 | Alpha | TS23871 | TEAMPRO Website | Need to change Header size to small and In Common pages need to change images related to that website | TBA | 2 |  | Medium
21 | Alpha | TS23893 | Taihan_ERP_01.10.2024 | Taihan Meeting with arif sir - 20/08/26 | TBA | 2 |  | High
22 | Alpha | TS23894 | Norden_ERP_01.05.21 | When requests such as leave applications or work-from-home (WFH) submissions are raised, the system is not sending automatic email notificat | TBA | 1 |  | Medium
23 | Alpha | TS23895 | Norden_ERP_01.05.21 | Employee, Mr. Saranraj E (Employee ID: 1-01-109), who is the HOD, is currently unable to approve leave requests submitted by the employees u | TBA | 0.75 |  | Medium
24 | Alpha | TS23756 | JGB_ERP_Implementation_30/05/25 | Auto allocation of Annual Leave not working | TBA | 0.75 |  | Medium

## Charlie
CHARLIE - DSR - 18/8
S.No | Team | ID | Project Name | Subject | CB | ET | RT | Priority | Current status | AT taken | AT% | P% | E%
1 | Charlie | TS23789 | Project Library | Frappe Framework Training- 1 | JH | 8 | 5.21 | Medium | Pending Review | 3.18 | 39.75 | 46.48% | 61.04%
2 | Charlie | TS23850 | Internal ERP - TEAMPRO V15 | Bio Metric Registration for TFP employee | JH | 2 | 2 | Medium | Working | 0 | 0
3 | Charlie | TS23851 | Internal ERP - TEAMPRO V15 | Assets Send to New Employee | JH | 1 |  | High | Working | 0 | 0
4 | Charlie | TS23738 | Aramm HR_SALESPRO_18.08.26 | Lead Fields update and Give a separate data import tool with the template | JH | 4 | 4 | Medium | Working |  | 0
5 | Charlie | TS23748 | KBL_HRMS 2nd Phase_02.04.2025 | Chief executive officeneed to come below the signature in Performance Improvement Plan print | SM | 0.5 | 0.5 | Medium | Client Review | 0.41 | 82 | 84.71% | 100%
6 | Charlie | TS23818 | KBL_HRMS 2nd Phase_02.04.2025 | BGV entry could not be found on BGV portal Job application ref: Nesanoor Rajashekar, Kushankumar K and Praveen S | SM | 0.75 | 0.43 | High | Client Review | 0.36 | 48
7 | Charlie | TS23854 | KBL_HRMS 2nd Phase_02.04.2025 | The attached undertaking form to be replaced in the set of post joining documents. | SM | 0.5 | 0.5 | Medium | Client Review | 0.57 | 114
8 | Charlie | TS23861 | KBL_HRMS 2nd Phase_02.04.2025 | For this Staff KSL1750, leave accruals are not updated need to check | SM | 0.5 | 0.5 | Medium | Client Review | 0.53 | 106
9 | Charlie | TS23860 | Hindustan Academy_ERP_06.11.2024 | Need to correct the Outstanding amount in Fees | SM | 0.25 | 0.25 | High | Completed | 0.25 | 100
10 | Charlie | TS23856 | TSA_BLR_HRPRO_03/07/23 | For 6th Aug OT created for all employees | SM | 0.75 | 0.75 | High | Completed | 0.72 | 96
11 | Charlie | TS23879 | Internal ERP - TEAMPRO V15 | Provide access for the document type "Candidate List" in Data Import | SM | 0.25 | 0.25 | Urgent | Completed | 0.21 | 84
12 | Charlie | TS23752 | IR India HRPRO Implementation | the employee takes leave,lop,absent for more than 3 consecutive days, an email notification should be sent to us on the third day. | SM | 1.5 | 1.5 | Medium | Pending Review | 1.58 | 105.3333
13 | Charlie | TS23875 | Johoku_01.07.2022 | Attendnance Summary is not visible for JMPLS209 | SM | 0.75 | 0.75 | Medium | Pending Review | 0.8 | 106.6667
14 | Charlie | TS23665 | QPIC_ERP_10.04.22 | Qty are not refetced in Technical Sheet_PE-TS-PE-BAG-2026-00033_ Material Combination | SM | 0.75 |  | Medium | Working | 0 | 0
15 | Charlie | TS23846 | QPIC_ERP_10.04.22 | Need to update the Machinery values which given in excel | SM | 1.5 | 0.98 | Medium | Working | 0 | 0
CHARLIE - DPR - 19/8
S.No | Team | ID | Project Name | Subject | CB | RT | Total RT | Priority
1 | Charlie | TS23738 | Aramm HR_SALESPRO_18.08.26 | Lead Fields update and Give a separate data import tool with the template | JH | 1.77 | 7.77 | Medium
2 | Charlie | TS23898 | Project Library | Frappe Framework-2 | JH | 6 |  | Medium
3 | Charlie | TS23876 | Johoku_01.07.2022 | On duty Application is Approved , But still the attendance is showing Absent Status. | SM | 0.5 | 5.98 | Medium
4 | Charlie | TS23878 | KBL_HRMS 2nd Phase_02.04.2025 | Need to correct the Leave balance for given employee as per the attached sheet | SM | 2.5 |  | Medium
5 | Charlie | TS23665 | QPIC_ERP_10.04.22 | Qty are not refetced in Technical Sheet_PE-TS-PE-BAG-2026-00033_ Material Combination | SM |  |  | Medium
6 | Charlie | TS23845 | QPIC_ERP_10.04.22 | Need to cross check the Item Master sheet and upload the Items | SM | 2 |  | Medium
7 | Charlie | TS23846 | QPIC_ERP_10.04.22 | Need to update the Machinery values which given in excel | SM | 0.98 |  | Medium